## Sheet1
Developer | Bronson Billing (575952)
Project | KIT205 Assignment 1 - Database
Description | Database implementation where two data structures are compared with each other for performance. This particular project involves a database of UFC fighters and event codes.
GitHub | https://github.com/BronsonKBilling/KIT205_575952
Start Date | 2025-04-13
| Milestone Description | GitHub Commit Dates | Functions implented/updated | Resources Used | Test Functions | Implementation/Testing Notes
| Linked list implementation for strings to be used for book borrower list | 29/07/2024 1/08/2024 | new_list insert_at_front print_list delete_from_list destroy_list | ChatGPT used to speed implementation of C string functions https://www.geeksforgeeks.org/c-program-to-implement-singly-linked-list/ See code comments for further details | linked_list_test - tests insertion in empty and large linked lists; deletion from the front, middle, and rear | Had issue where random characters were printed. Used breakpoints and watches to identify that new_list was not correctly initialised.
| Not a milestone - Created all necessary functions and files for implentation of prototype 1, a linked list within a linked list. | 2025-04-19 | create_record compare_records print_records test_records create_list print_list print_one_to_many insert test_list | Adapted tutorial code, mainly from the week 6 tutorial. Also used ChatGPT to learn about generic types (void*) | test_records - Tests all functions of the records file. Not yet implemented test_list - Tests all functions of the linked_list file. Not yet implemented | These functions have not been implemented. The only implemented function among those listed is create_list(), as this was easily adapted from the tutorial code. This commit is to give a structure and a plan for my future development of the first prototype. It aims to be the scaffolding for the prototype and prove that I have thought about how I wish to implement it before actually implementing it.