## Sheet1
Developer | Bronson Billing (575952)
Project | KIT205 Assignment 1 - Database
Description | Database implementation where two data structures are compared with each other for performance. This particular project involves a database of UFC fighters and event codes.
GitHub | https://github.com/BronsonKBilling/KIT205_575952
Start Date | 2025-04-13
| Milestone Description | GitHub Commit Dates | Functions implented/updated | Resources Used | Test Functions | Implementation/Testing Notes
| Linked list implementation for strings to be used for book borrower list | 29/07/2024 1/08/2024 | new_list insert_at_front print_list delete_from_list destroy_list | ChatGPT used to speed implementation of C string functions https://www.geeksforgeeks.org/c-program-to-implement-singly-linked-list/ See code comments for further details | linked_list_test - tests insertion in empty and large linked lists; deletion from the front, middle, and rear | Had issue where random characters were printed. Used breakpoints and watches to identify that new_list was not correctly initialised.
| BST implementation for books. BST nodes contain the book title as well as linke list of strings for borrowers. | 5/8/2024 8/8/2024 | new_book (empty list of borrowers) new_bst insert_bst (sorted by book title) delete_bst destroy_bst find_bst print_bst(initial implementation) | Just adapted tutorial code to use strings, borrower list is just set to NULL | bst_test - tests insertion to the left, insertion to the right, and large number of random insertions (see rand_string function for generating test strings); test deletion for zero, one and two child case, and deletion of the root. | Noticed that program crashed on destroy_bst. Did not occur for an empty bst, so checked memory allocations and discovered error with malloc in insert_bst. Noticed an issue when book titles have spaces - decided to just remove spaces for now, may fix later.