## Sheet1
Developer | Bronson Billing (575952)
Project | KIT205 Assignment 2 - Graph
Description | Routing protocol demonstration comparing how quickly two shortest path algorithms (Dijkstra's and Bellman-Ford) reach convergence in a simulated network. This compares the algorithms used in two routing protocols, the now dated RIP (Bellman-Ford) and the dominant OSPF (Dijkstra).
GitHub | https://github.com/BronsonKBilling/KIT205_575952
Start Date | 2025-05-20
| Milestone Description | GitHub Commit Dates | Functions implented/updated | Resources Used | Test Functions | Implementation/Testing Notes
| Milestone - Finished implementing algorithm comparison function. Both algorithms are compared to eachother to see how quickly they can build a full routing table for each device on the network. Also added helper function to delete network and free memory. This marks the point where all code for the assignment has been completed. | 2025-06-05 | delete_network test_network compare_algorithms | ChatGPT was used to generate python code that was used to generate network files for algorithm comparison. | test_network - This function was changed slightly to free dynamically allocated memory at the end of its execution. This is needed as the comparison function runs right after it. | I also cleaned up quite a bit of the code and added comments to functions that needed them. I had far less commits with this assignment compared to the last one, I believe a large reason for this was due to my development practices getting better. There were far fewer mistakes that needed correcting with this function, and I made sure that functions were maintainable and readable as I was writing them, rather than last time when I needed to make multiple correction commits.
| Milestone - Finished implementing tests for the Bellman-Ford algorithm function. It has been thoroughly tested along all execution paths and potential network conditions. This means that both algorithms have been implemented and comparisons can begin | 2025-06-04 | find_shortest_paths_bellman_ford print_routes print_routes_from_test_file test_network | ChatGPT was used for troubleshooting code issues | test_network - The function now tests The Bellman-Ford algorithm function and sees if it can accurately build routing tables for different network conditions. All execution paths are reached by the tests. Extra tests were also added for build_routing_table_from_distances, which was added in the previous commit | Tests were heavily refactored in this commit. The tests (especially printing expected and actual routes) had code duplication between them, so helper printing functions were added to remedy this.
| Not a milestone - Completed implementation of Bellman-Ford algorithm and separated the routing table building part of both the dijkstra function and the Bellman-Ford function to a separate helper function | 2025-06-03 | find_shortest_paths_bellman_ford build_routing_table_from_distances | ChatGPT was used to make pseudocode that helped me to learn about the Bellman-Ford algorithm, also helped with basic debugging | test_network - This function does not fully test the Bellman-Ford function yet, it just does a basic adhoc test to see if the function actually works | The code for both the Dijkstra and Bellman-Ford algorithm could use further refactoring to avoid code duplication. The easiest of which has already been done, which was moving the routing table building to build_routing_table_from_distances
| Milestone - Dijkstra's algorithm function for building a routing table has been completed as the testing function has now implemented tests for it. The tests go through every execution path and realistic case for a computer network | 2025-06-03 | test_network find_shortest_paths_dijkstra add_link all_devices_known | ChatGPT was used minimally for debugging, and it was used to come up with ideas for test cases. | test_network - Executes every possible execution path of all functions in the network.c file. It tests all likely and allowed network configurations that could be fed into find_shortest_paths_dijkstra. | In addition to completing the testing function, I needed to make fixes to other functions and needed to correct some oversights made in prior commits.
| Not a milestone - Completed implementation of Dijkstra's algorithm and its associated helper functions. Completed implementation of main routing table builder function | 2025-06-01 | build_routing_tables find_shortest_paths_dijkstra all_devices_known | ChatGPT was used to check whether my implementation of Dijkstra's algorithm was correct or not. It discovered two minor errors that it helped to fix. Notes taken from the weekly content that focused on Dijkstra's algorithm were used for building the implementation of th algorithm | test_network - The functions that were implemented in this commit have not yet been tested. The point at which they are tested will mark a milestone | I also added a file that contains the full routing table for all 'devices' in the test_graph file. This commit made use of my notes on the weekly content, then my implementation based on that content was assessed by ChatGPT for accuracy.
| Not a milestone - Changed graph data structure to suit use case of a computer network | 2025-05-24 | add_edge build_graph_from_file test_graph | ChatGPT was used for some debugging | test_graph - Modified to suit new header file and datastructure changes | Added routing table to graph/network
| Milestone - First commit, basic graph data structure has been implemented as an adjacency list and graph functions pass tests | 2025-05-20 | add_edge build_graph_from_file test_graph main | ChatGPT was used once for debugging. The graph data structure was taken and adapted from the week 9/10 tutorials | test_graph - Tests the two graph functions and their potential execution paths. Both of these functions are not complex and do not have many execution paths, so tests were minimal | This commit just included an adaptation of the week 9/10 tutorial code with updated tests. It also saw the graph data structure being placed in its own file. This file will be expanded to accommodate the project and its comparisons.