## Sheet1
Developer | Bronson Billing (575952)
Project | KIT205 Assignment 1 - Database
Description | Database implementation where two data structures are compared with each other for performance. This particular project involves a database of UFC fighters and event codes.
GitHub | https://github.com/BronsonKBilling/KIT205_575952
Start Date | 2025-04-13
| Milestone Description | GitHub Commit Dates | Functions implented/updated | Resources Used | Test Functions | Implementation/Testing Notes
| Not a milestone - Regenerated data for testing. Prior dataset was not large enough for any meaningful tests as the M and N values were just too small. | 2025-04-30 | generate_ufc_dataset_to_file() | ChatGPT was used to write the entirety of the python data generation file | N/A | ChatGPT created all code to generate the dataset. Previous data is still held in the repo as an artifact and can still be used for testing, it is just not suitable for doing any meaningful tests of the prototypes.
| Not a milestone - Added a python file that was used to turn data from dataset into a format that can be used for testing the database functions and data structures. | 2025-04-29 | main() (data_creator.py) | ChatGPT was used to help create the regular expression that matches if a record has the format 'UFC [event code]' Kaggle was used to retrieve a dataset of all UFC events from 1996-2024. This is the dataset that is modified to create the testing dataset. The link for this dataset is: https://www.kaggle.com/datasets/maksbasher/ufc-complete-dataset-all-events-1996-2024?resource=download | N/A | Dataset was taken from Kaggle (more information in resources used section) and converted into testing data using Python script. The output of the Python script is now in the file 'data.txt' while the original dataset is in the file 'medium_dataset.csv'.
| Milestone - Fully implemented all functions in database.c by testing them thorougly along all execution paths. The database has now been fully implemented and both the many to many and one to many relationships can be printed successfully. Some funcitons in database.c have also been modified, mainly to make them more user friendly by giving helpful messages. | 2025-04-29 | test_database print_events_of_fighter_avl print_events_of_fighter_list print_events_of_fighter add_fighter_avl add_fighter_list add_fighter_to_event | No other resources were used for this commit. | test_database - This function is now fully implemented and tests all functions in database.c along all possible execution paths. | While the assignment spec does not say to have the database be made to accommodate users, the theme of the entire project for me has been to accommodate a potential upgrade of the program to accommodate user input and usage. This is why the database will give helpful error messages and will say what it is printing prior to printing it. This decision also informed my data structure choices.
| Not a milestone - Implemented functions for database.c. Also made changes to avl_tree to accommodate the database better. linked_list had a function name refactored as well for clarity | 2025-04-27 | insert_list print_avl_node_without_tree print_avl_without_tree print_events print_fighters_in_event add_fighter_list add_fighter_avl add_fighter_to_event add_event print_events)of_fighter_list print_events_of_fighter_avl print_events_of_fighter test_database | No other resources were used for this commit. | test_database - This currently only includes unstructured adhoc tests that aimed to prove that the functions work in their most basic use cases. Functions in database.c require further testing | It has become obvious across multiple files that the commenting style is somewhat inconsistent. There is (I feel) a good amount of comments written, but the style of them and the display needs to be made uniform. There are also some functions that have far less commenting than others. A commit will need to focus solely on updating comments. It has also come to my attention that my use of a doubly linked list may have been somewhat unnecessary. It was meant to cut down the time it takes to search for records. But later on I realised that it would be pointless when searching for fighters, as the alphabetical order of names can be quite random. I found that it would only be useful for searching from the tail or head of the list that contains event codes, as if the tail was an event such as 315, and the user was searching for event 310, then it can be easily calculated that it would be better to go from the tail. However the most time complex function of the database, which is finding which events a fighter has fought in, requires every event to be searched. This means that the usefulness of the doubly linked list is lessened.
| Milestone - Fully implemented all function in avl_tree.c by testing them thoroughly along all possible execution paths. This means that prototype 2 data structures are now implemented. | 2025-04-25 | get_avl_node_height insert_avl_node delete_avl delete_avl_children test_avl | ChatGPT was used sparingly for some basic bug finding. As this assignment grows my knowledge of both C and Visual Studio testing tools, I am relying less and less on resources for fixing my code. I find it easier now to fix it myself and often find ChatGPT's suggestions to be a hinderance and incorrect. The tutorials also were used and tests written for the week 5 tutorial on BSTs were retrofitted for testing AVLs. | test_avl - Fully implemented. Now tests all execution paths and possible scenarios. There are many notes justifying certain decisions within this test function. | Now that this file has been fully implemented. The record and linked_list files can be expanded to incorporate this file.
| Not a milestone - Implemented all functions aside from test_avl in avl_tree.c. Also created a header file for it. | 2025-04-24 | create_avl find_avl_node find_avl find_left_right_height get_avl_node_height left_rotate right_rotate balance_tree insert_avl_node insert_avl print_avl_node print_avl test_avl | The tutorials, specifically the week 5 tutorial on BSTs, were used heavily. Code was copied from it, and functions were derivative of it. ChatGPT was used for gaining a slightly better understanding of how balancing the tree could be implemented but for the most part the balancing and insertion methods were derived from my notes on the weekly content. | test_avl - not fully implemented. Only holdds adhoc tests | test_avl has been implemented with some adhoc tests that served purely to see the basic functionality of the functions. These are by no means exhaustive and do not at all match the format seen in other testing functions. This file also has more code from the tutorials than any other file. Both the linked list and record files were largely implemented with very little tutorial code and were largely custom. This file also uses a similar format of having wrapper functions and a wrapper struct as the BST file did in the week 5 tutorial.
| Milestone - Implemented all functions linked_list.c and implemented a testing function. All tests passed and this compiled successfully. This means that all prototype 1 data structures have been created | 22/04/2025 20/04/2025 | create_node insert_at_front insert_at_rear insert_at_middle_from_front insert_at_middle_from_rear insert delete_node test_list | ChatGPT was used to again learn more about memory and pointers. It was used to a far lesser extent than in previous commits. The tutorial code was also used as both a reference for the code and was partially directly used. | test_list - Tests all functions in linked_list.c that need testing (notes about this are present in the function). The tests go through all possible execution paths and ensure that the functions work as intended | Some functions need to make assumptions and these are noted in the comment headers of the functions. These assumptions reflect things that take place upstream of the function, normally things that have been planned for the database implementation.
| Not a milestone - Implemented new functions in Record.c and fixed existing functions | 2025-04-22 | compare_records print_records clone_record destroy_record change_int_identifier change_string_identifier test_record | ChatGPT was used to troubleshoot errors and gain a better understanding of memory management and how pointers work. Was also used to gain an understanding of how I could test destroy_record. It helped me come to the conclusion that the funciton had been tested enough and that no further testing could be done | test_record - Now tests the new functions. Existing tests have been modified to incorporate the new functions | This change was necessary to ensure memory safety and scalability with the database. This commit especially aided my understanding of C and how memory works within C, and on a hardware level in general. I feel far more confident using C after this commit. This file will need to be expanded further in the future once the AVL tree is implemented, in order to incorporate the ability for Records to store lists and trees within their data field.
| Not a milestone - implemented all functions aside from test_list in linked_list.c | 2025-04-20 | print_list insert_at_front insert_at_rear insert_at_middle_from_front insert_at_middle_from_rear insert | ChatGPT was used to troubleshoot an error. The error blocked Record values from being accessed within linked_list. The compiler stated that Record was an 'incomplete type' and any attempt to access elements within Record was impossible. ChatGPT was used but was not helpful and couldn't accurately find the error. I had to do so myself | None implemented so far | Error checking in some functions is left bare. This may look alarming but the errors that may be encountered in these functions, such as in insert(), are handled either upstream or downstream of the functions.
| Milestone - Implemented all functions in 'record.c' and implemented a testing function. This compiled and all tests passed | 2025-04-19 | create_record compare_records print_records test_records | ChatGPT was used to troubleshoot some errors. Also was used to gain a further understanding of enums, particularly why they cannot be set to NULL. | test_record - Tests all functions in 'record.c' file. Tests that error checks within these functions work as intended and that all execution paths are valid and work properly | Had an issue where enums could not be null. I needed to change the implementation of how enums are used in records by creating an 'unset' option. This commit shows up in the Github history as being made on the 20th of April, but it was originally made on the 19th. The commit message did not include 'MILESTONE' and needed to be reworded, this resulted in the date being changed.
| Not a milestone - Created all necessary functions and files for implentation of prototype 1, a linked list within a linked list. | 2025-04-19 | create_record compare_records print_records test_record create_list print_list print_one_to_many insert test_list | Adapted tutorial code, mainly from the week 6 tutorial. Also used ChatGPT to learn about generic types (void*) and enums. | test_record- Tests all functions of the records file. Not yet implemented test_list - Tests all functions of the linked_list file. Not yet implemented | These functions have not been implemented. The only implemented function among those listed is create_list(), as this was easily adapted from the tutorial code. This commit is to give a structure and a plan for my future development of the first prototype. It aims to be the scaffolding for the prototype and prove that I have thought about how I wish to implement it before actually implementing it.